## Sumary
Version 1.2
2016-10-21
VietSoftware International
CURRENCY SWAP

## Change
History
No. | Create | Version | Date | Description
1 | Nguyễn Danh Tháp | Version 1.0 | 2016-10-07
2 | Nguyễn Danh Tháp | Version 1.1 | 2016-10-07
3 | Nguyễn Danh Tháp | Version 1.2 | 2016-10-21

## Schedule
1. Schedule
[22 empty] | : | Holiday |  |  |  |  | ▼ | : Release sprint | [8 empty] | : | Timeline Testing | [7 empty] | : | Timeline UAT
[21 empty] | : | Timeline Release 1 | [6 empty] | : | Timeline Release 2 | [7 empty] | : | Timeline Release 3 | [7 empty] | : | Finished
| Currency Swap |  |  |  |  | 2016-10-01 | [7 empty] | 2016-11-01 | [29 empty] | 2016-12-01
 | time axis 2016-10-24 to 2016-12-18
Requirements and environment | bar: 2016-10-24 to 2016-10-28; 2016-12-03 to 2016-12-04; 2016-12-10 to 2016-12-11; 2016-12-17 to 2016-12-18
Release 1 | bar: 2016-10-31 to 2016-11-04; 2016-11-07 to 2016-11-11; 2016-11-14 to 2016-11-15; 2016-12-03 to 2016-12-04; 2016-12-10 to 2016-12-11; 2016-12-17 to 2016-12-18
Release 2 | bar: 2016-11-16 to 2016-11-18; 2016-11-21 to 2016-11-25; 2016-12-03 to 2016-12-04; 2016-12-10 to 2016-12-11; 2016-12-17 to 2016-12-18
Release 3 | bar: 2016-11-28 to 2016-12-11; 2016-12-17 to 2016-12-18
Testing | bar: 2016-11-07 to 2016-11-11; 2016-11-14 to 2016-11-18; 2016-11-21 to 2016-11-25; 2016-11-28 to 2016-12-11; 2016-12-17 to 2016-12-18
UAT | bar: 2016-12-03 to 2016-12-04; 2016-12-10 to 2016-12-18
Finished | bar: 2016-12-03 to 2016-12-04; 2016-12-10 to 2016-12-11; 2016-12-16 to 2016-12-18
2. Note
|  | Requirements & Environment |  | 2016/10/24~ 2016/10/28
Pre-condition: Signed Contract, provided Git information and Server Information
- KickOff Project
- Requirement Analystic
- Project configuration
- Initialize Redmine
- Initialize Git Respository
- Setup Server Enviroment
|  | Release 1 |  | 2016/10/31 ~ 2016/11/15
Pre-condition: Confirmed Requirement
Sprint 1
Design
Database
Project Struct
Supporting Script
Security Layer
Layout
UI Layout Frame
Menu/Navigation
Sprint 2
Users
Login/Logout
Register
User Profile & Avatar
Approve Registered User
User Tabs
User List
Save Action
Forget Password
Auto Block User when Date Expired
|  | Release 2 |  | 2016/11/14 ~2016/11/25
|  |  | Sprint 3 | 2016/11/14 ~2016/11/18
Enhancement Release 1
Orders
New Order
Search Matching Orders
Submit Action
Swap Action
|  |  | Sprint 4 | 2016/11/21 ~2016/11/25
Order Details
Activity Logs
Confirm Action
Cancel Action
Clear Action
Order Tabs: Working Orders, Submited Orders, History
|  | Release 3 |  | 2016/11/28~2016/12/09
|  |  | Sprint 5 | 2016/11/28 ~2016/12/02
Support
Support Form
Help
Support Message Management
|  |  | Sprint 6 | 2016/12/05 ~2016/12/09
Notification
Quick View
Full View
Notification on All actions
|  | Testing |  | 2016/11/07~2016/12/06
|  | UAT |  | 2016/12/07~2016/12/17
|  | Finished |  | 2016/12/17